## Sheet1
Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
Anirudh Kompella | - Created project proposal document outlining system design and objectives - Researched Catapult C conversion from C++ to Verilog | -Created IO Devices Presentation - Implemented calibration mode (SW[8]) with center sampling + RGB capture -Wrote Verilog Tests for top Layer + Developed microarchitecture for color capture logic | -Designed and implemented the snake block module with core logic -Implemented two-flip-flop CDC synchroniser for all camera-to-VGA domain signals (top level) -Added rendering system for snake game visuals | - Created comprehensive snake Game test file - Ran Snake Game logc into vidis HDL and generated Verilog files for top level | -Developed capstone website showcasing team and project -Maintained site with updates, progress, and resources -Engineered brightness threshold to reject near-black false-positive matches (with Chance) | -Created comprehensive testbenches for key modules validating correct hardware behaviour - Implemented frame divider to control snake movement speed precisely | - Implemented a 20x15 grid canvas using single-bit FPGA registers in draw game - Built hand detection integration using centroid coordinates from color_detect - Designed three-priority pixel renderer for cursor, painted cells, background | - Built catch game with real-time hand tracking - Designed dynamic difficulty scaling using score thresholds - Implemented VGA pixel renderer with custom glyphs | - Updated catch game with pseudo-random object spawning via LFSR logic - Rendered scaled bitmap glyphs for live scoreboard and win banner for Pong game - Written comprehensive testbench for all the games
Chance Howarth | - Implemented 32×32 block-based color detection and RGB averaging across the frame - Built accumulator system per block column for true frame-based processing - Computed block coordinates and transitioned to frame-based detection pipeline | -Built on-screen calibration UI (center box + indicators) -Displayed live and captured RGB values on HEX + debug outputs -Added LED indicators and refined exposure controls | -Routed I2C interface to configure D5M camera sensor registers over SCLK -Developed visual overlay (tracking box + center marker) -Added real-time debugging visuals (live RGB, tracking feedback) | - Designed and implemented game mode (black screen + tracked white dot) - Added top-level mux to switch between camera and game display pipelines -Integrated zoom mode and control refinements | -Developed bounding box output to localise the detected colour region -Engineered brightness threshold to reject near-black false-positive matches (with Anirudh) -Designed tolerance scaling system that adapts to varying lighting conditions | -Developed frame buffer to stabilise and improve real-time camera tracking -Debugged key hardware modules and testbenches to ensure correct functionality | - Fixed inverted direction tracking on draw game - Synthesized design using 300 flip-flops sharing the 25 MHz VGA clock | - Built two-player hand-tracked Pong using colour detection and VGA output - Implemented signed velocity ball physics with per-hit speed acceleration - Rendered scaled bitmap glyphs for live scoreboard and win banner | - Implemented Bresenham line algorithm for smooth strokes in draw game - Created pencil sprite with pen-state colour feedback in draw game - Refined 2 color tracking for the Pong game.
Amer Salem | -Created Project Outline | -Researched HLS tools -Diagrammed, described, and mapped modules and I/O ports | -Validated snakegame and made sure it was HLS friendly -Created module slides -Integrated top level with current completed modules | - Created SnakeWrapper to map Snake_top Level for Top level - Ran Snake Game logc into vidis HDL and generated Verilog files for top level | -Broke down the complex snake game into simple snake -Implemented, verified, and tested snake movement, food spawn, and snake growth. -Looked into pixel warping issue | -Updated the Snake game to allow right to left tracking - Added game states and a start screen | - Added Score Tracking into FSM and UI Component to snake Game - Implemented head-relative dead zone to prevent unintended direction changes - Created deterministic food sequence cycling through ten pre-set grid positions | - Instantiated separate renderer module keeping game logic cleanly decoupled | - Created a poster with clear sections covering algorithms, rendering, and peripherals
Munasib Ilham | -Looked into hardware architecture design for our project | -Built initial top level code for FPGA interface -Developed microarchitecture for color capture logic | -Created micro architecture Diagram and Slides -Developed graphics rendering pipeline for the game |  |  |  | - Optimized Snake game to Compile faster - Looking at ways to fix synchronization issue between VGA clock speed and verilog module clock speed | -Added Game Over UI | - Writing the final report