## Sheet1
Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
Anirudh Kompella | - Created Project Proposal document - Researched Catapult C conversion from C++ to Verilog | -Created IO Devices Presentation - Implemented calibration mode (SW[8]) with center sampling + RGB capture -Wrote Verilog Tests for top Layer | -Designed and implemented the snake block module -Developed core snake game logic -Added rendering system for snake game visuals | - Created Snake Game test file - Ran Snake Game logc into vidis HDL and generated Verilog files for top level | -Developed capstone website showcasing team and project -Maintained site with updates, progress, and resources | -Created testbenches for key modules -Debugged Key modules and test benches | - Implemented a 20x15 grid canvas using single-bit FPGA registers in draw game - Built hand detection integration using centroid coordinates from color_detect - Designed three-priority pixel renderer for cursor, painted cells, background
Chance Howarth | - Implemented 32×32 block-based color detection and RGB averaging across the frame - Built accumulator system per block column for true frame-based processing - Computed block coordinates and transitioned to frame-based detection pipeline | -Built on-screen calibration UI (center box + indicators) -Displayed live and captured RGB values on HEX + debug outputs -Added LED indicators and refined exposure controls | -Developed visual overlay (tracking box + center marker) -Added real-time debugging visuals (live RGB, tracking feedback) | - Designed and implemented game mode (black screen + tracked white dot) - Added top-level mux to switch between camera and game display pipelines -Integrated zoom mode and control refinements |  | -Developed buffer to improve camera tracking -Debugged Key modules and test benches | - Fixed inverted direction tracking on draw game - Synthesized design using 300 flip-flops sharing the 25 MHz VGA clock
Amer Salem | -Created Project Outline | -Researched HLS tools -Diagrammed, described, and mapped modules and I/O ports | -Validated snakegame and made sure it was HLS friendly -Created module slides -Integrated top level with current completed modules | - Created SnakeWrapper to map Snake_top Level for Top level - Ran Snake Game logc into vidis HDL and generated Verilog files for top level | -Broke down the complex snake game into simple snake -Implemented, verified, and tested snake movement, food spawn, and snake growth. -Looked into pixel warping issue | -Updated the Snake game to allow right to left tracking (done) - Added game states and a start screen (done) - Adding collision logic and a game end state (in-progress) | -Added Game Over UI -Added Score Tracking into FSM and UI Component
Munasib Ilham | -Looked into hardware architecture design for our project | -Built top level code for FPGA interface -Developed microarchitecture for color capture logic | -Created micro architecture Diagram and Slides -Developed graphics rendering pipeline for the game |  |  | - Optimized Snake game to Compile faster - Looking at ways to fix synchronization issue between VGA clock speed and verilog module clock speed | -Added a Leaderboard ranking system with functional UI